## Sheet2
Ministry of Energy and Water Resources
Somali Electricity Recovery Project
Project Implementation Unit (PIU)
PRE-BID CONFERENCE
HEALTH FACILITIES - BRA/GL/SW/HR/JL - 22 July 2024
ITEM NO. | BID REFERENCE | ITEM DESCRIPTIONS | RESPONSE FROM PIU/MINISTRY
Procurement Clarifications
1 | Deadline for submission of bid(ITB 23.1) | We kindly request an extension of minimum four (4) weeks for international submission of bids, this will give the bidders the sufficient time to submit their most competitive proposal, ensuring best value to the employer. | The project is behind schedule and due to that the Ministry can no longer extend the submission deadline. Therefore all bidders are encourage to submit their bids as per the submission deadlines stipulated in the bid document. No further extension granted.
2 | Form of submission (ITB 22.1) | Considering the delivery challenges and extended delivery times experienced with courier services like DHL Express and TNT, could we explore the possibility of submitting bids electronically to ensure efficiency and timeliness? | No electronic submissions are accepted. The Ministry shall not take the responsibility of any bids submitted through courier services such as DHL. Only bids submitted physically to the Ministry's offices shall be considered for evaluations.
3 | Operations and Maintenance (O&M) Costs | How does the O&M cost be factored in after the initial 2 years O&M Services. | The quoted price for the O&M services shall remain the same throughout if the contract for the services needs to be extended beyond the currently estimated 2 years.
4 | Contractors associations | How is the JV Partnership is being evaluated with regard to their roles | Bidders shall refer to the pages of 58-68 under section III about Evaluation and qualification criteria
5 |  | The Bidders are required to attach Award letters and completion certificates for the previous and current projects. We require clarification if both the award letters and completion certificates are required for each project or if either will suffice. | Submission of both the award letters and the completion certificates are required. For the ongoing contracts, award letters suffices.
6 |  | Bidders are required to provide Statutory documents (registration and certification documents), Should the documents be certified by a commissioner of oaths? | Registration and certification documents of eligible countries of Bank financed operations are acceptable.
7 | ITB 11.2 (I)-(a) | Submissions shall be properly bound, paginated, initialized and serialized without any loose pages. | This shall strictly be complied with by bidders to safeguard bid's integrity
Technical Clarifications
|  | Qn1. Some of the facilities are not found from manual google earth search - Can the ministry provide the coordinates | Refer to the ESMP reports attached in the MoEWR Website.
7 |  | Qn2. PV Mounting Structures - Requesting the ministry to specify the type of PV mounting structures to be used for each facility either ground / roof mounting or guarantee availability of land for areas where roof space is not enough for recommended solar capacity | The type of Mounting Structure required for PV panels shall be clear to the contractor upon conducting site surveys at the design stages in preparation of the detailed design submission for approval.This probably shall occur upon awarding the bid to a successful contractor. At the bid stage, it is highly recommended for the bidders to make their own arrangement to visit sites to appraise themselves the site conditions and requirement.
8 |  | For places with both solar and ground PV mounting structures, the ministry should specify the recommended height for the ground mount solar, for example carport | The bid is design and build. What the MoEWR has provided in the bid is preliminary design data in assissting the bidders to come up with their bid. The responsibility of detailed design lies with the successful bid. In terms of minimum recommended clearance of Solar PV from ground is specified in the bid.
9 |  | Power-room - is the bidder expected to provide power rooms even for the smaller systems or will the education facilities provide space for the inverters/ battery packs applies to 60kW and 20kW systems | It is the responsibility of the bidder to provide it.
10 |  | Incoterms CIP - Ministry to confirm if they will be responsible for payment of taxes for imported materials quoted under CIP incoterms. | Contractors are responsible of paying all duties, levies, taxes and any other forms of charges applicable to the goods required for the accomplishment of the project as shown per ITB 17.5 (d)
11 |  | Technical bid submissions the bidder is expected to submit "Detailed design of the proposed system showing all necessary technical assumptions applied, calculations, system sizing, spare capacity, projected system losses etc. The design shall cover the major equipment/devices including Modules, Arrays, Mounting Module Structures, Combiners, Inverters, Battery Inverters, Batteries, Communication & Monitoring system, Switchgears, Protection, Earthing and Lightning Protection, Cables (both DC & AC), HVAC system and any other system required to make the plant functional. Bidders to submit electrical schematic diagram of the proposed PV systems design and configuration showing the main equipment/components and control equipment/switchgear, their interconnection, and the power flows. One diagram for EACH type of facility; Ministry of Education, University, Teacher Training Colleges, and Schools." - | Data given specifically that of capacity shall suffice at the moment in coming with the preliminary design of various lots and categories
12 |  | Requesting the ministry to provide load profiles for the facilities to enable detailed designs and calculations required above | Bidders are urged to use the current provided preliminary information to come up with required bid preliminary design concept. Detailed design shall be undertaken by the successful bidder after award of the bid
13 |  | Is electronic bid submission an option for this bid | Not allowed as shown ITB 23.1 in the BDS
14 |  | System Topology - Is the system topology 3 - phase or single phase? | For bigger system it is strictly Three Phase. Smaller system- it depends on existing site conditions
15 |  | Security - For facilities without fences , is the bidder expected to fence the entire facility or only the area with the PV system? | Contractors is supposed to take care and provide round the clock security protection measures to the location of the plant.
16 |  | Design of System control and data acquisition (SCADA) systems for General Hospitals, Maternity Hospitals and Health Centers including production of drawings | It refers to the various education facilities and other associated Ministries buildings not Health Facilities. This scope is strictly for education facilities and associated institutions
17 |  | Installation, testing and commissioning of System control and data acquisition (SCADA) and peripherals equipment technical specifications for hospitals | It is the SCADA provisions which will allow system monitoring and control both locally and remotely
18 |  | Site location coordinates if available | Refer to various ESMPs attached in the Ministry's Website
19 |  | What are the critical load requirements for Ministry of Education, Teachers training colleges and schools, TTC and Schools Request for battery autonomy/battery providing number of hours/battery dependencies | In the preliminary design at the bid stage, let bidders use the provided capacity for both PV system and BESS
20 |  | What is the acceptance and Invoicing criteria for the entire project | Refer to the payment terms as shown in the proposed contract clause 2 and Terms & Procedures of Payments